## Sheet1
TASKS | Start Date | End Date | Duration | Member name
Research phase | 2023-04-21 08:00 | 2023-04-21 17:00 | 1 day
Researching the main components. | 2023-04-21 08:00 | 2023-04-21 17:00 | 1 day | Amira Azouz
Checking the OWASP standards. | 2023-04-21 08:00 | 2023-04-21 17:00 | 1 day | Iheb Zitouni
Review existing research and literature on password security best practices. | 2023-04-21 08:00 | 2023-04-21 17:00 | 1 day | Ines Afli
Overview of main existing solutions | 2023-04-28 08:00 | 2023-04-28 17:00 | 1 day
Research the existing solutions for password strength testers and assess their strengths and weaknesses. | 2023-04-28 08:00 | 2023-04-28 17:00 | 1 day | Iheb Zitouni
Explore the algorithms and techniques for Password Strength Testers. | 2023-04-28 08:00 | 2023-04-28 17:00 | 1 day | Amira Azouz
Identify areas for improvement and differentiation in the proposed solution. | 2023-04-28 08:00 | 2023-04-28 17:00 | 1 day | Ines Afli
Develop a High-Level Design Document for the Password Strength Tester | 2023-05-04 08:00 | 2023-05-04 17:00 | 1 day
Create a list of functions from the user perspective. | 2023-05-04 08:00 | 2023-05-04 17:00 | 1 day | Ines Afli
Create a list of functions from the system perspective. | 2023-05-04 08:00 | 2023-05-04 17:00 | 1 day | Amira Azouz
Create a design reference document for the development. | 2023-05-04 08:00 | 2023-05-04 17:00 | 1 day | Iheb Zitouni
Develop the web application | 2023-05-08 08:00 | 2023-05-11 17:00 | 4 days
Creating the structure of our web application page using HTML. | 2023-05-08 08:00 | 2023-05-11 17:00 | 4 days | Ines Afli
Designing the visual appearance using CSS. | 2023-05-08 08:00 | 2023-05-09 17:00 | 2 days | Amira Azouz
Write JavaScript code to handle the password strength checking. | 2023-05-08 08:00 | 2023-05-11 17:00 | 4 days | Iheb Zitouni